## Slide 2: San Pedro Creek Status Update
Phases 1.1 and 1.2 Construction
Phase 1.2 Design
Phase 1.2 Design and Construction timelines
Project Partner Coordination

## Slide 3: PROJECT PHASING

## Slide 4: DESIGN ENHANCEMENTS
CONSTRUCTION UPDATE

## Slide 5: Phase 1.1 Construction Update
  Sundt-Davila JV on schedule to complete construction of Phase 1.1 by May 5, 2018
  Flagstone in manantial area
  Limestone for 12 generation benches and in pools
  Landscaping in Santa Rosa to Martin block
  Travis Gatehouse concrete poured
  Last public construction tour conducted on February 2

## Slide 14: Phase 1.2 Construction Update
Early Work Package 11
  Former Dollar General building demolition to begin February 19
  Utility relocations ongoing
Early Work Package 12
  Demolition and heavy civil work to begin in March
Full construction projected to begin in late summer or early fall

## Slide 15: DESIGN ENHANCEMENTS
DESIGN UPDATE

## Slide 16: Phase 1.2 Design Update
Design team working towards 90% submittal on February 28
  Focus on Houston to Commerce block
    Water wall feature
    Entertainment plaza
100% design submittal due May 31
Coordination with SDJV ongoing

## Slide 17: Phase 1.2 Timeline
100% submittal May 31
90% submittal Feb 28
Guaranteed Maximum Price July 31
Begin Full Construction Late Summer
Begin EWP Construction in February
Construction Completion Mid-2020

## Slide 18: Partner Coordination
Commissioners Court
  Jan 30: Approval of O&M Agreement between Bexar County, The City of San Antonio, and the San Antonio River Authority
City Council
  Feb 8: Approval of Temporary Construction Easements
SARA Board
  Jan 17: Approval of budget amendment for Work Packages 11 & 12

## Slide 19: Partner Coordination
Executive Committee
  David Smith, County Manager, Bexar County
  Lori Houston, Assistant City Manager, City of San Antonio
  Mike Frisbie, Director, Transportation and Capital Improvements, City of San Antonio
  Suzanne Scott, General Manager, San Antonio River Authority
Jan 9: Regular Monthly Meeting

## Slide 20: DESIGN ENHANCEMENTS
QUESTIONS
& COMMENTS

## Slide 21
SAN PEDRO CREEK ARTS
Program Update

## Slide 22: WORD ART
Word Art installed
Investigating paint infill
Notes: You may recall, I showed this to you last time
On the left are approved mock ups
On the right is a mold for the manantial tile (blue tile)

## Slide 23
TILE MURALS
All five murals are in production
Studio visit February 20-21
Installation begins in March
Notes: And last time you had requested an overview the locations of the Menchaca tiles. I’ve indicated them here in light blue (click 5 times)

## Slide 24: PROGRAMMING
Calendar of events
  Regular tours (Art and History)
  Temporary art installations
  Site appropriate events
Arts & Culture Alliance meeting – March 13
  Partnerships with local arts organizations
  Sponsorship and grant opportunities

## Slide 25: DESIGN ENHANCEMENTS
QUESTIONS
& COMMENTS