## Slide 1
February 14, 2019

## Slide 3: Updates
Phase 1.1
  Remaining items
Phase 1.2
  Construction activities
  Partner coordination
  Additional Funding
Phases 1.3 and 2
  Design Activities

## Slide 4: Phase 1.1 Remaining Items
Additional railing at Travis Gatehouse
  Installation to begin in late February
Inlet lighting
Trash screen at inlet pump station
Santa Rosa Pedestrian Crossing

## Slide 5: Phase 1.2 Construction
Early Work Package 11: Demolition and utility relocation
  Water & gas work on Dolorosa ongoing
  Three north lanes closed for 6-8 weeks
Early Work Package 12: Heavy civil construction
  Drilled shaft installations between Commerce and Nueva
  Concrete pours in Houston to Commerce block
Early Work Package 13: Commerce Street bridge deck and Penner’s parking
  Bridge deck being constructed

## Slide 12: Phases 1.3 and 2 Design

## Slide 13: Phase 1.3 and Phase 2 Design
  Kickoff meeting held on January 17
    Design guidelines established
  Value Engineering efforts ongoing
  Mario Schjetnan to be engaged to review and consult
  Desired design completion October 2019

## Slide 14: Partner Coordination
SAISD administration building
  SARA/SAISD coordination
Camaron Street construction
  COSA 95% plans provided to contractor
  Travis to Houston block to be completed in May
  Remainder to begin in late winter 2019
Alameda Theater
  Project team coordination
Texas Public Radio
  Demolition started
  Coordination ongoing

## Slide 15: Partner Coordination
Commerce Street
  Construction Proposals under review
  Construction to begin May/June
UTSA downtown campus expansion
  SPC design files shared
  Coordination meeting to scheduled
Federal Courthouse (GSA)
  Coordination ongoing

## Slide 16: Partner Coordination
Executive Committee
  David Smith, County Manager, Bexar County
  Lori Houston, Assistant City Manager, City of San Antonio
  Razi Hosseini, Interim Director, Transportation and Capital Improvements, City of San Antonio
  Suzanne Scott, General Manager, San Antonio River Authority
Next Meeting – February 27

## Slide 17
QUESTIONS
& COMMENTS